## S&P
Committee | Project Name | Project Scope (overview) | Project Task List (action items, people and deadlines) | Potential Outputs (capabilities, ROI, success factors) | Value Proposition Alignment | Project Lead | Project Team | Expected Completion Date | Date Completed | Rollout Plan
Standards & Practices (S & P) | Business Metrics Resource | Create a business metrics spreadsheet with examples of metrics and industry verbiage. | Collect metrics, KPIs, SLAs from a variety of sources. Review and create a document or dictionary for our members to reference as needed. Make searchable? Allow members to comment on specific examples and/or add others? | Examples of KPIs, SLAs and general dictionary of terms within industry is posted and available for members to review. | 1, 4, 5 | Brian Bules | Tara Cassady, Amy Josephson | 2020-12-01 | 2020-10-01 | Include in content library of assn website as well as the HRPC.
Standards & Practices (S & P) | PROJECT: HR Procurement Center (HRPC) website and resource development | The HR Procurement Center will be the world’s first virtual HR marketplace, serving as an official listing, purchasing service and resource guide for the evalutaion, selection, implemenation and program management of outsourced, HR service provider programs. Information, tools and resources will be segmented into the following sub-project categories: EVALUATION (identifying the need to outsource) SELECTION (selecting the right partner) IMPLEMENTATION (managing the transition) PROGRAM MANAGEMENT (ongoing management of the program/partnership) SAMPLE FORMS/POLICIES PROGRAM MANAGEMENT RESOURCES | This project will be broke into 6 project teams (as outlined below) and each will create a detailed project plan, TO-DO list, owners and deadlines for their team's project. 1. EVALUATION: Buying Process Considerations-How to evaluate readiness/Need to outsource 2. SELECTION: Tools to explore/select vendors (RFI, determining the scope) and the RFP process (sample RFPs, how to manage process,how to evaluate, selecting finalists for onsite presentations, who to include in these meetings, corp communication at this stage and making your final selection) 3. IMPLEMENTATION: Managing the Transition/Implementation of a Program (with your new partner) 4. PROGRAM MANAGEMENT: Tools to work with and manage the partnership 5. SAMPLE FORMS/POLICIES: Contracts, Metrics (SLAs, KPIs), Process Maps, Organizational Charts with/without Blended Model, project time line, project scope, etc. (examples of different forms/processes/policies, instructions, definitions, etc.) 6. PROGRAM MANAGEMENT RESOURCES (Communication Templates (Commuication to Board/Leaders/Employees/Providers/Community/Customers), Quarterly/Annual Business (Partnership) Review, Buyer FAQs, etc.) | Provide a proficient procurement process to streamline purchasing, ensuring that buyers pay the best price for goods and services and save time by choosing from only the most reputable vendors – HRO Today Certified Providers. Offer several best practices, how to guides and resources to assist HR buyers throughout the processes of: evaluation/identifying need to outsource, selecting a vendor, implementing the program, managing the program, sample forms/policies and program management resources. | 1, 2, 3, 4, 5 | Brian Bules/Jen Knippenberg/Jason Munoz/Zachary Misko |  | 2021-09-01
Standards & Practices (S & P) | sub-project for HR Procurement Center (HRPC) website and resource development EVALUATION | EVALUATION: Buying Process Considerations-How to evaluate readiness/Need to outsource | confirm readiness/need to outsource (questionaire) building your case for the Board/c-suite reviewing and selecting potential partners Communication Components |  | 1, 3, 4, 5 | Jason Munoz |  | TBD |  | Submit all project outputs to RP and EHC to review and cosideration in adding some or all components to the HRPC website.
Standards & Practices (S & P) | sub-project for HR Procurement Center (HRPC) website and resource development SELECTION | SELECTION: Tools to explore/select vendors (RFI, determining the scope) and the RFP process (sample RFPs, how to manage process,how to evaluate, selecting finalists for onsite presentations, who to include in these meetings, corp communication at this stage and making your final selection) | RFI and/or RFP?: Which one should be the first step and what do you include? Evaluating written responses from potential partners In person final selection interviews (format, participants, evaluation and selection) Communication Components Contract completion |  | 1, 3, 4, 5 | Brian Bules |  | TBD |  | Submit all project outputs to RP and EHC to review and cosideration in adding some or all components to the HRPC website.
Standards & Practices (S & P) | sub project for HR Procurement Center (HRPC) website and resource development IMPLEMENTATION | IMPLEMENTATION: Managing the Transition/Implementation of a Program (with your new partner) | Discovery/Training with new partner Creating a project plan Communication Components |  | 1, 3, 4, 5 | Jen Knippenberg |  | TBD |  | Submit all project outputs to RP and EHC to review and cosideration in adding some or all components to the HRPC website.
Standards & Practices (S & P) | sub-project for HR Procurement Center (HRPC) website and resource development PROGRAM MANAGEMENT | PROGRAM MANAGEMENT: Tools to work with and manage the partnership | Setting expectations of SLAs/KPIs through reporting (what, frequency, measure of satisfaction) |  | 1, 3, 4, 5 | Zachary Misko |  | 2021-06-30 |  | Submit all project outputs to RP and EHC to review and cosideration in adding some or all components to the HRPC website.
Standards & Practices (S & P) | sub-project for HR Procurement Center (HRPC) website and resource development SAMPLE FORMS/POLICIES | SAMPLE FORMS/POLICIES: Contracts, Metrics (SLAs, KPIs), Process Maps, Organizational Charts with/without Blended Model, project time line, project scope, etc. (examples of different forms/processes/policies, instructions, definitions, etc.) | Value Stream Mapping Utilizing LEAN Sample KPIs/SLAs |  | 1, 3, 4, 5 | Brian Bules/Jen Knippenberg/Jason Munoz/Zachary Misko |  | 2021-06-15 |  | Submit all project outputs to RP and EHC to review and cosideration in adding some or all components to the HRPC website.
Standards & Practices (S & P) | sub-project for HR Procurement Center (HRPC) website and resource development PROGRAM MANAGEMENT RESOURCES | PROGRAM MANAGEMENT RESOURCES Communication Templates: -Commuication to Board, Leaders, Employees, Providers, Community, Customers) -Quarterly/Annual Business (Partnership) Review -Buyer FAQs Managing Gen 2 | Templates/Examples of communication used throughout the process Examples of program dashboards Buyer FAQs |  | 1, 3, 4, 5 | Brian Bules/Jen Knippenberg/Jason Munoz/Zachary Misko |  | 2021-06-15 |  | Submit all project outputs to RP and EHC to review and cosideration in adding some or all components to the HRPC website.
Standards & Practices (S & P) | PROJECT: HR Technology Tools (What? When? Why? How To?) | Create an HR Systems and Tools Digital/Technology List (websites, mobile apps, technology platforms/systems, techology providers, self-service and light-service HR and Staffing tools, ie. ServiceNow, CRM, Workday, LinkedIn, etc.) and Functionality Guide (when, why and how to best leverage) for HR professionals. | Create listing of digital/technology tools, platforms, self/light service, mobile apps, and websites available for Human Resource purposes. Provide information about each of these in terms of when, why and how to use them(purpose, functionality, best practices, etc.) Enable search fucationality feature to allow search by competency, topic, name, type of resource, etc) | Provide a reference guide for members to evaluate all of the different techology/digital tools, platforms and resources available in the HR marketplace, with information on when, why and how to use these and ensure you select what's best for your organization. | 1,3,4,5 | Brian Bules |  | 2021-12-01 |  | Publish HR Systems and Tools Digital/Technology List and Functionality Guide to association website as resource for members. Introduce to members in monthly newsletter, Presidents message , Member Meet-Up and online via social media channels to promote this new member resource.
Standards & Practices (S & P) | PROJECT: HRO Today Association Resource/Content Library | MEMBER RESOURCES (CONTENT) LIBRARY - REVIEW AND UPGRADES: Improve the current online content library in terms of quality/quantity of documents/resources available to members. | Devise a better system to request, receive and organize content library for members and enable search functionality on the HRO Today Association Website. How do other associations manage this? (gather intel from at least 3 other assns) Can we/do we track usability? (determine if our website/technology currently has fuctionality to track views/downloads of the resources/content available to members. If so, what is tracked and how?) Designate resource categories to enable members to easily find what they are looking for. (ie. sample policies, sample forms/documents, org charts, process maps, white papers, case studies, articles, presentations, etc. (are these the right categories? what is missing?) Expand promotion of online content library by contributing blogs, articles, columns, etc. to be featured in HRO Today online universe. Committee members would also encourage others (peers, colleagues, clients, partners) to submit content. Use social media to blog/post about new content and/or content needed, as a way to support and advertise the online content. | 1. Provide a diverse level of resources avaialable to members (sample forms/policies, case studies, white papers, process maps, SOPs, etc.) 2. Ensure portal is easy to navigate and search for content. 3. Better process to call for/collect content. | 3, 4, 5 | Zachary Misko |  | 2021-12-01

## MBR REL & ENG
Committee | Project Name | Project Overview | Project Task List (action items, people and deadlines) | Potential Outputs (capabilities, ROI, success factors) | Value Proposition Alignment | Project Lead | Project Team | Expected Completion Date | Date Completed | Rollout Plan
Member Resources & Engagement | Mentorship Program | Develop online program for connecting newer members with more experienced members to assist with onboarding to the Association. Also connect those who are new to the HR profession to those with more experience. |  | Increased engagement of both new and more experienced members; members-only benefit adds value to membership | 1,2,3
Member Resources & Engagement | Member Directory Enhancement | Incorporate skills inventory/demographics into the online member directory so users can create more comprehensive profiles, which in turn can help generate more targeted connections. Research and implement more advanced technology/tools to make creation of profiles easier for members and to give the directory a more sophisticated look and feel. |  | Eaiser and more meaningful networking among members; ability to gather data on member preferences related to professional development (e.g., topics and skill levels) | 2,3
Member Resources & Engagement | HRO Today/Association website | Provide ongoing feedback on the HRO Today site to ensure the member user perspective is incorporated into content and design. |  | Ongoing improvement of overall site related to content and functionality to increase traffic; inclusion of members-only content and features to add value to membership | 1,2,3,5
Member Resources & Engagement | Association Discussion Forum | Assist with creating an online destination for members looking to connect with peers to ask/answer questions and share information. Committee members would serve as moderators with an expectation to visit the forum a few times a week to post content and to comment on other posts. |  | Members-only benefit adds value to memnbership; increased member engagement; ability to mine conversations in forum to generate professional development resources | 2,3
Member Resources & Engagement | Livestream Calendar | Assist with building the schedule for 2022 by suggesting topics and presenters, including inviting colleagues and clients to participate. Assist with promotion by sharing posts on social media and forwarding email invites. |  | More targeted livestream offerings to bring larger, more engaged audiences | 1,3
Member Resources & Engagement | Association Awards Program | Leverage award nominations to produce a catalog of best practices and create a livestream series | Review submissions from award finalists and winners over the past 3 yeara to select those to feature in the best practices catalog (inclusion not guaranteed to all finalists); select finalists and winners to be part of awards livestream series, invite participants, and serve as hosts/noderators of livestream sessions | Engage award participants in award programs "after the win"; extend recognition of award finalists and winners; generate topics for livestream series; create an online catalog of best practices as another members-only benefit | 1,3,5
Member Resources & Engagement | Content Generation | TO BE LED BY S&P COMMITTEE; MOVED TO THEIR PROJECT PLAN